## Ark1
Lofthus Frukt og Saft | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Tasks
Meeting with client | Week 1: Andrea
Research | Week 2: Andrea, John,; Week 3: Phillip
Preperation work | Week 3: John
Designing | Week 4: John, Mary,; Week 5: Silje
Testing | bar: Week 5 to Week 6
Presentation for client | Week 7: Andrea
Discussing and revisiting | bar: Week 7
Launching Website | Week 8: John